## Sheet0
ID | Project ID | Project Name | Key ID | Key | Issue Type ID | Issue Type | Category ID | Category Name | Version ID | Version | Subject | Description | Status ID | Status | Priority ID | Priority | Milestone ID | Milestone | Resolution ID | Resolution | Assignee ID | Assignee | Create User ID | Created by | Created Date | Due date | Update User ID | Updated by | Updated | Attachment | Shared File
3640150 | 68218 | ATM Project | 19 | ATM_1-19 | 292180 | Bug |  |  | 63737 | 1.1 | Incorrect amout being added to account | Depositing into any account on card 1 the system is accepting a valid input to insert into the account when depositing into checking or savings for card 1 The amount displayed as Total balance on the account should be the increased amount correctly The amount shown is $0.10 less than the expected amount ex. $9.90 instead of $10 | 1 | Open | 3 | Normal | [6 empty] | 319498 | LAB1-438 | Jan. 21, 2022 16:32 |  | 319498 | LAB1-438 | Jan. 21, 2022 16:32 | 0 | 0
3636944 | 68218 | ATM Project | 1 | ATM_1-1 | 292180 | Bug |  |  | 63671 | 1.0 | Depositing into savings | Testing depositing functionality Card 1 inserted and in the deposit menu for savings Tried to deposit $50.00 into savings Should deposit $50.00 to card 1 Says the overall balance is now $1040.00, ten dollars less and says card 2 instead | 3 | Resolved | 3 | Normal | [6 empty] | 319498 | LAB1-438 | Jan. 20, 2022 12:16 |  | 319498 | LAB1-438 | Jan. 21, 2022 16:27 | 0 | 0
3636950 | 68218 | ATM Project | 2 | ATM_1-2 | 292180 | Bug |  |  | 63671 | 1.0 | ATM 1.0 Inputting Transaction type | Tested inputting transaction type functionality Card 1 inserted and on the choose transaction type menu Tried to input an invalid transaction type Should do nothing or display invalid transaction type Puts 20.00$ on screen Defect still exists in version 1.1 only for key 5 now | 2 | In Progress | 3 | Normal | [6 empty] | 319498 | LAB1-438 | Jan. 20, 2022 12:21 |  | 319498 | LAB1-438 | Jan. 21, 2022 16:25 | 0 | 0
3636975 | 68218 | ATM Project | 4 | ATM_1-4 | 292180 | Bug |  |  | 63671 | 1.0 | ATM 1.0 Incorrect Card number displayed | On any transaction when the receipt is being displayed The system is serving a customer The error appears when the transaction prints on the screen when you do any transaction The expected outcome is the correct card number being displayed For Card 1 the output was Card 2 For Card 2 the output was Card 3 There seems to be a +1 added to the card number Defect still exists in version 1.1 | 2 | In Progress | 3 | Normal | [6 empty] | 319498 | LAB1-438 | Jan. 20, 2022 12:35 |  | 319498 | LAB1-438 | Jan. 21, 2022 16:24 | 0 | 0
3636978 | 68218 | ATM Project | 6 | ATM_1-6 | 292180 | Bug |  |  | 63671 | 1.0 | Checking money market balance | Testing check balance for money market accepting a transaction request select check balance for money market on card 1 should display the correct balance, $5000.00 by default instead displays $1000.00 and says an unknown error occurs while a $500 symbol slowly grows in. Fixed in version 1.1. | 3 | Resolved | 3 | Normal | [6 empty] | 319498 | LAB1-438 | Jan. 20, 2022 12:37 |  | 319498 | LAB1-438 | Jan. 21, 2022 16:23 | 0 | 0
3636976 | 68218 | ATM Project | 5 | ATM_1-5 | 292180 | Bug |  |  | 63671 | 1.0 | Incorrect withdrawal amount | Tested withdrawal functionality Card 1 inserted and withdrawal menu for savings Tried to withdraw $200.00 Should withdraw $200.00. 100 bills were put into ATM. WIthdrew $20.00 and display that. | 3 | Resolved | 3 | Normal | [6 empty] | 319498 | LAB1-438 | Jan. 20, 2022 12:35 |  | 319498 | LAB1-438 | Jan. 21, 2022 16:23 | 0 | 0
3636980 | 68218 | ATM Project | 7 | ATM_1-7 | 292180 | Bug |  |  | 63671 | 1.0 | Balance Inquiry | Testing writing to receipt Card 2 inserted Requested to perform Balance Inquiry on Money Market Nothing was written to receipt, and user was prompted if they wanted to perform another transaction Transaction should have printed to the receipt box and the user is shown the balance and available money. Fixed in version 1.1. | 3 | Resolved | 3 | Normal | [6 empty] | 319498 | LAB1-438 | Jan. 20, 2022 12:40 |  | 319498 | LAB1-438 | Jan. 21, 2022 16:20 | 0 | 0
3636999 | 68218 | ATM Project | 9 | ATM_1-9 | 292180 | Bug |  |  | 63671 | 1.0 | Withdrawal from savings on card 1 | Card 1 inserted. 200 bills in ATM. Withdrawing $20.00 withdraws $40.00, withdrawing $40.00 withdraws $60.00, withdrawing $60.00 gives withdraws $100.00, withdrawing $100.00 withdraws $200.00 and withdrawing $200.00 withdraws $20.00. Fixed in version 1.1 | 3 | Resolved | 3 | Normal | [6 empty] | 319498 | LAB1-438 | Jan. 20, 2022 12:56 |  | 319498 | LAB1-438 | Jan. 21, 2022 16:15 | 0 | 0
3637005 | 68218 | ATM Project | 11 | ATM_1-11 | 292180 | Bug |  |  | 63671 | 1.0 | Typo | When it asks for another transaction, it says "wood" instead of "would" | 3 | Resolved | 3 | Normal | [6 empty] | 319498 | LAB1-438 | Jan. 20, 2022 13:00 |  | 319498 | LAB1-438 | Jan. 21, 2022 16:12 | 0 | 0
3640140 | 68218 | ATM Project | 18 | ATM_1-18 | 292180 | Bug |  |  | 63737 | 1.1 | Typo with withdrawal | When withdrawing from a savings account on card 2, the prompt for 60 dollars says 60 instead of $60 | 1 | Open | 3 | Normal | [6 empty] | 319498 | LAB1-438 | Jan. 21, 2022 16:11 |  | 319498 | LAB1-438 | Jan. 21, 2022 16:11 | 0 | 0
3637026 | 68218 | ATM Project | 12 | ATM_1-12 | 292180 | Bug |  |  | 63671 | 1.0 | Daily withdrawal limit exceeded | Withdrawing more than $300 from any account The system is serving either card number 1 or card number 2 When withdrawing more than $300 the screen show the daily withdrawal limit exceeded Since there is nothing on the requirements that say that there should be any withdrawal limit then we are expecting no withdrawal amount limit. Bug still exists in version 1.1. | 2 | In Progress | 3 | Normal | [6 empty] | 319498 | LAB1-438 | Jan. 20, 2022 13:14 |  | 319498 | LAB1-438 | Jan. 21, 2022 16:11 | 0 | 0
3637028 | 68218 | ATM Project | 13 | ATM_1-13 | 292180 | Bug |  |  | 63671 | 1.0 | Transfer from money market to chequing on card 2 | Card 2 inserted, transfer from money market to chequing. Tried to transfer $4.00, transferred $3.50. Tried to transfer $10, transferred 9.50$. | 3 | Resolved | 3 | Normal | [6 empty] | 319498 | LAB1-438 | Jan. 20, 2022 13:15 |  | 319498 | LAB1-438 | Jan. 21, 2022 16:06 | 0 | 0
3640074 | 68218 | ATM Project | 14 | ATM_1-14 | 292180 | Bug |  |  | 63671 | 1.0 | Transfer bug on card 1 and card 2 | Any transfers on card 1 involving the money market account displays "invalid account type" and any transfers on card 2 involving the savings displays "invalid account type". Balances on all accounts were above $0.00. 200 bills input to ATM. Defect still exists in version 1.1 | 2 | In Progress | 3 | Normal | [6 empty] | 319498 | LAB1-438 | Jan. 21, 2022 14:58 |  | 319498 | LAB1-438 | Jan. 21, 2022 16:06 | 0 | 0
3640116 | 68218 | ATM Project | 15 | ATM_1-15 | 292180 | Bug |  |  | 63671 | 1.0 | MFT: Transfer display bug | MFT: Testing: Transfer Card 1 transferring from chequings to savings Steps to reproduce: transfer from chequings to savings on card 1 Expected: displays transferring from chequings to savings Actual : displays transferring from savings to chequings. Defect still exists in version 1.1 | 2 | In Progress | 3 | Normal | [6 empty] | 319498 | LAB1-438 | Jan. 21, 2022 15:35 |  | 319498 | LAB1-438 | Jan. 21, 2022 16:04 | 0 | 0
3640131 | 68218 | ATM Project | 17 | ATM_1-17 | 292180 | Bug |  |  | 63671 | 1.0 | MFT: Asking for correct PIN twice | MFT: When the card is inserted and the system is asking for a PIN The system is waiting for user input When entering a wrong PIN (either once or twice) and then entering the correct PIN when the correct PIN is inputted then the accounts should be displayed There is another screen that appears where it asks for the PIN once more. Still exists in version 1.1 | 2 | In Progress | 3 | Normal | [6 empty] | 319498 | LAB1-438 | Jan. 21, 2022 15:57 |  | 319498 | LAB1-438 | Jan. 21, 2022 16:03 | 0 | 0
3640118 | 68218 | ATM Project | 16 | ATM_1-16 | 292180 | Bug |  |  | 63671 | 1.0 | MFT: Incorrect inquiry account displayed on Card 1 | MFT: Balance inquiry being tested the system is asking which account to show the inquiry for Display error only happens on card 1 when asking for a balance inquiry The account should display Checking and Savings accounts Accounts listed as Checking and Money Market Still exists in version 1.1 | 2 | In Progress | 3 | Normal | [6 empty] | 319498 | LAB1-438 | Jan. 21, 2022 15:41 |  | 319498 | LAB1-438 | Jan. 21, 2022 16:02 | 0 | 0